PROVIDENCE HOUSING AUTHORITY

FACILITIES MANAGEMENT

Board of Commissioners subcommittee meeting

Capital Improvements

July 23, 2020

Major Projects Underway

- The new tot lot at Hartford Park is 100% complete; this was funded through CDBG and CFP funds.

- A bid package is currently advertised to install a young adult fitness park at Chad Brown; this is funded with a $33,000 check presented by Councilman Narducci, CDGB and CFP funds.

- Construction to vinyl side 4 bldgs. at Hartford and 6 duplexes at Scattered Sites is in progress.

- The Authority has procured a roof consultant to assess the roof conditions all bldgs. at Chad and Hartford; a full report was received. All the roofs on the Chad Brown side and Sunset Village need to be replaced; roofs on the Admiral Terrace side and Hartford have 2-3 years left before replacement.

- Further information will be provided in the Monthly Management Report.

- The Authority has applied for CDBG money with the COP to replace the sliding doors at Dexter, Parenti and Kilmartin; CFP funds will be needed to supplement the project.

- The Kilmartin elevator modernization project has begun and is in progress; this project will resume shortly.

- A contract has been awarded to replace the apt. entrance door locks at Manton; construction date will be determined due to COVID-19.

- The fire alarm/sprinkler installation project at 335 Hartford is approximately 98% complete; completion of this project is expected to be extended due to COVID-19.

- A bid package was awarded to install automatic sprinklers and fire alarm upgrades to Carroll Towers, Parenti Villa and Dexter Manor; start of construction has been postponed due to COVID-19.

- The Lead Consultant has reviewed all the lead test results and is currently creating the scope of work. This project will be funded through a $975,000 lead grant awarded by HUD for Hartford, Chad/Ad/Sun and Manton; CFP funds will also be used for this project.

- A contract has been signed to replace the roof at 335 Hartford H-rise; replacement is expected to begin August/Sept.

- A contract has been signed to install panic bar hardware on all common stairwell doors at Dexter I and II; funding will be CDBG from the City of Prov. and CFP funds.

- A vendor has been selected for a professional design for emergency generator transfer switch and emergency generator interface system at the Tavares Center at Chad Brown and the community room at 144 Dodge St.

- A low bidder has been identified for elevator modernization at 335 Hartford; a contract has been signed.

- Porch and h-cap ramp replacement at 3 Scattered Site duplexes is in progress.