PROVIDENCE HOUSING AUTHORITY

FACILITIES MANAGEMENT

Board of Commissioners subcommittee meeting

Capital Improvements

September 24, 2020

Major Projects Underway

- A bid package is currently advertised to replace all the roofs at Chad Brown and the roof at Sunset Village.

- The roof replacement at 335 Hartford is in progress; this should take approximately 6 weeks for completion.

- A bid package is currently advertised to install the new outside patio seating are at 50 Laurel Hill.

- A bid package is currently advertised to install new security cameras on the exterior of Parenti Villa; this is partially funded through a CDBG grant from the City of Prov. and CFP funds.

- Further information will be provided in the Monthly Management Report.

- The Authority has applied for CDBG money with the COP to replace the sliding doors at Dexter, Parenti and Kilmartin; CFP funds will be needed to supplement the project.

- A contract has been awarded to replace the apt. entrance door locks at Manton; construction date will be determined due to COVID-19.

- The fire alarm/sprinkler installation project at 335 Hartford is approximately 98% complete; completion of this project is expected to be extended due to COVID-19.

- A bid package was awarded to install automatic sprinklers and fire alarm upgrades to Carroll Towers, Parenti Villa and Dexter Manor; start of construction has been postponed due to COVID-19.

- The Lead Consultant has reviewed all the lead test results and is currently creating the scope of work. This project will be funded through a $975,000 lead grant awarded by HUD for Hartford, Chad/Ad/Sun and Manton; CFP funds will also be used for this project.

- A contract has been signed to install panic bar hardware on all common stairwell doors at Dexter I and II; funding will be CDBG from the City of Prov. and CFP funds.

- A vendor has been selected for a professional design for emergency generator transfer switch and emergency generator interface system at the Tavares Center at Chad Brown and the community room at 144 Dodge St.

- A low bidder has been identified for elevator modernization at 335 Hartford; a contract has been signed.

- A bid package is currently advertised to install a young adult fitness park at Chad Brown; the Authority received a sole bid of $296,000 which is way over original budget. The Authority will discuss further options.

- The Elevator modernization project at Kilmartin Plaza has resumed; 1 elevator car is close to completion.

- Vinyl siding 4 bldgs. at Hartford and 6 duplexes at Scattered Sites is in progress; 2 bldg. at Hartford are 99% complete.

- The porch and handi-cap replacement project at 3 Scattered Site Duplexes are in progress.