PROVIDENCE HOUSING AUTHORITY

FACILITIES MANAGEMENT

Board of Commissioners subcommittee meeting

Capital Improvements

December 10, 2020

Major Projects Underway

- Chad Brown roofing project has been awarded and is under way.  Work on 35 March, 61 March, and 65 March has begun.  Estimated time of completion is early Spring 2021

- With help from CDBG funds from the Providence City Council, PHA can upgrade a computer server and add several cameras at Carroll Tower.  This is a collaboration between the City of Providence and PHA

- Dominica Manor is in the process of receiving all three boilers through the efforts of RISE Engineering.  RISE is covering all costs associated with the project.

- Deck and ramp replacements at Scattered Sites are about 85% complete.

- The lock replacement project at Manton Heights is 100% complete.  All residents received new locks and keys over the course of about 3 weeks.

- Further information will be provided in the monthly MMR report

- Roof replacement at 335 is near completion.  The Hi-rise roof has been replaced.  We are currently waiting for materials to arrive to complete the lower roof overhang in front of the lobby at 335.

- Kilmartin elevator project continues.  The first car is nearing completion as it is 90-95% done.  As soon as it is complete work will begin on the second car.

- Dominica Sprinkler System is 100% complete.

- Sprinkler Systems at Carroll Tower, Parenti Villa, and Dexter Manor are now in the beginning stages of work.  As of right now only work in common areas is happening.

- Exterior siding projects at Hartford Park and Scattered Sites is expected to be completed by November 30, 2020.

- The Authority has applied for CDBG money with the COP to replace the sliding doors at Dexter, Parenti and Kilmartin; CFP funds will be needed to supplement the project.

- The fire alarm/sprinkler installation project at 335 Hartford is approximately 99% complete; this project has resumed and is expected to be completed within 2 months.

- The Lead Consultant has reviewed all the lead test results and is currently creating the scope of work. This project will be funded through a $975,000 lead grant awarded by HUD for Hartford, Chad/Ad/Sun and Manton; CFP funds will also be used for this project.

- A contract has been signed to install panic bar hardware on all common stairwell doors at Dexter I and II; funding will be CDBG from the City of Prov. and CFP funds.

- A vendor has been selected for a professional design for emergency generator transfer switch and emergency generator interface system at the Tavares Center at Chad Brown and the community room at 144 Dodge St.

- A low bidder has been identified for elevator modernization at 335 Hartford; a contract has been signed.

- A bid package is currently advertised to install a young adult fitness park at Chad Brown; the Authority received a sole bid of $296,000 which is way over original budget. The Authority has discussed further option with Councilman Narducci; a meeting is set for Nov. 1 to further discuss options.

- A bid package is currently advertised to install the new outside patio seating are at 50 Laurel Hill.